## Gantt Chart Template
Gantt Chart Template
Project Name:
| Task Name | Start (Date) | End (Date) | Duration (Days)
| Data collection | 2024-01-08 | 2024-01-15 | 6
| Data pre-processing | 2024-01-16 | 2024-01-25 | 9
| Data analysis | 2024-01-16 | 2024-01-30 | 14
| Data splitting | 2024-01-31 | 2024-02-08 | 8
| Traning dataset | 2024-02-09 | 2024-02-23 | 14
| Traning model | 2024-02-24 | 2024-03-04 | 8
| Testing dataset | 2024-03-05 | 2024-03-18 | 12
| Evauation method | 2024-03-19 | 2024-04-01 | 13

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.
Of course, if you need to manage your projects online, in real-time, click the link to the right-----> where you can start your 30-day Free Trial!